## Sheet1
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2021-09-14 | 2021-09-21 | 2021-09-28 | 2021-10-05 | 2021-10-12 | 2021-10-19 | 2021-10-26 | 2021-11-02 | 2021-11-09 | 2021-11-16 | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21
Project Phase | Activity | Task Owner Name | Start Date | End Date | Status | Progress %
Project Initiation | Discuss project proposals | ALL | 2021-09-14 | 2021-09-15 | Finished | 100%
Not Started | Confirm Project Team Roles | ALL | 2021-09-15 | 2021-09-16 | Finished | 100%
In Progress | Develop two business cases | Noah , Darsh Jalan | 2021-09-17 | 2021-09-21 | Finished | 100%
Finished | Develop Project Initiation Document(PID) | Aayushi Shah | 2021-09-21 | 2021-09-28 | Finished | 100%
Behind | Produce Initial Project Plan, RACI | Shreya Niphade | 2021-10-01 | 2021-10-05 | Finished | 100%
| Begin Home Page Development | Daksh Jasani | 2021-09-28 | 2021-10-05 | Finished | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements | Produce BRM diagram, define User Roles | Elsa Poonawala | 2021-10-05 | 2021-10-12 | Finished | 100%
Defination | Create Context Diagram and System Interface | Noah, Aayushi | 2021-10-05 | 2021-10-12 | Finished | 100%
Not Started | Define Business Requirements | All | 2021-10-05 | 2021-10-12 | Finished | 100%
In Pogress | Complete Requirements types | Aayushi, Elsa | 2021-10-12 | 2021-10-19 | Finished | 100%
Finished | Define Functional Decomposition | Darsh Jalan | 2021-10-12 | 2021-10-19 | Finished | 100%
Behind | Create RCT document | Darsh, Shreya | 2021-10-12 | 2021-10-19 | Finished | 100%
| Create Menu for Home Page | Daksh Jasani | 2021-10-12 | 2021-10-19 | Finished | 100%
| Decide which feature to implement this semester | ALL | 2021-10-19 | 2021-10-26 | Finished | 100%
| Use Case Diagram | Aayushi | 2021-10-19 | 2021-10-26 | Finished | 100%
| Activity Diagram | Elsa, Daksh | 2021-10-19 | 2021-10-26 | Finished | 100%
| Create analysis diagram (UML, DFD) | Shreya, Noah | 2021-10-19 | 2021-10-26 | Finished | 100%
| Complete Functional Requirements (User Stories) | Ajay, Darsh | 2021-10-19 | 2021-10-26 | Finished | 100%
| Home Page Demo Completed | Daksh Jasani | 2021-10-19 | 2021-10-26 | Finished | 100%
MILESTONE 2 : REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) | Noah Weitz | 2021-10-26 | 2021-11-09 | Finished | 100%
| Complete ER diagram and Database Table Specs | Shreya, Elsa, Aayushi | 2021-10-26 | 2021-11-09 | Finished | 100%
| Complete a physical Data-Flow diagram | Daksh, Shreya | 2021-10-26 | 2021-11-09 | Finished | 100%
| User Interface design | Darsh Jalan | 2021-11-09 | 2021-11-16 | Finished | 100%
| Establish Github Projects | Ajay Gupta | 2021-11-09 | 2021-11-16 | Finished | 100%
MILESTONE 3 : DESIGN COMPLETED
Implementation/Coding | User Portal GUI & Functional Design | Aayushi, Shreya | 2021-11-16 | 2021-11-30 | Finished | 100%
| Coding | Darsh, Ajay |  |  | Finished | 100%
| Create an Account | Ajay, Darsh | 2021-11-16 | 2021-11-30 | Finished | 100%
| Sign-in into Account | Ajay, Darsh | 2021-11-16 | 2021-11-30 | Finished | 100%
| User Table - Table Specification | Elsa | 2021-11-16 | 2021-11-30 | Finished | 100%
| Class Diagram (UML) | Shreya | 2021-11-16 | 2021-11-30 | Finished | 100%
| Complete Sequence Diagam | Daksh Jasani | 2021-11-16 | 2021-11-30 | Finished | 100%
| Source code uploaded to Github , executable code ready for testing | Ajay, Darsh | 2021-11-16 | 2021-11-30 | Finished | 100%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Complete Test Plan Document | Daksh | 2021-11-30 | 2021-12-07 | Finished | 100%
| Evaluate Features to be Tested | ALL | 2021-11-30 | 2021-12-07 | Finished | 100%
| Complete test design and test cases | ALL | 2021-11-30 | 2021-12-07 | Finished | 100%
| Execute Test Cases | ALL | 2021-11-30 | 2021-12-07 | Finished | 100%
| Analyze Test Results | ALL | 2021-11-30 | 2021-12-07 | Finished | 100%
MILETSONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation | ALL | 2021-12-07 | 2021-12-21 | Finished | 100%